## Slide 1: Transaction Management System (TMS) (formerly known as ATLAS)
September 2017, update

## Slide 2
Objectives
Goals
Approach
Milestones
Assumptions
Risks
Agenda

## Slide 3: Scope
Trading (Orders, Allocations, Trades )
Transfers
Cash Deposits, Withdrawals and Transfers
  Journals (addition of securities without specific trade attached)
Corporate Actions

## Slide 4: Goals
      Trade Content Management
                - Store and version full trade and asset lifecycle starting from Trade Capture and Position Impacts - Capture changes via business events for inbuilt audit
                - Store operational and process control of data
Explain impact of changes throughout lifecycle via Business Events
Maintain clear separation of Trade and Instrument (Deal Structure, Assets, Securities) data
Eliminate exising in-line Calc-Route calls
Provide managed storage and archival

## Slide 5: Objectives
Core TMS platform is ready to process, version and store the following;
  Ticket
  Allocations
  Trade and Cash Flows
  Position Impacts
TMS is asset agnostic which enables application teams to choose either an asset specific migration plan or to migrate business functions for all assets by transaction type.
Decommissioning of existing transaction (FTRNDB) will happen in late 2018 and throughout 2019

## Slide 6: Approach
Assess the current environment to migrate
Plan for a migration project
Architecting/decide a new target functional environment
Implementing a migration by using available tools and processes
Managing the newly migrated environment

## Slide 7: Goals
Milestone 1 - AIM Allocation Domain (Q4, 2017)
  Covers full lifecycle of allocation processing (from internal allocations to street side allocations and confirmations)
  Support upto 1000 Allocations/Block
  Status – Integration with AIM OMS and middle office functions, in-progress
Milestone 2 - Mid-office street-side Allocation (Q2, 2018)
  Provide mechanism to facilitate mid-office allocation processing
  Provide all allocations transactions for TC workflow
Milestone 3 - Confirmations (2018 Goal, TBD)
  Confirmation workflows and states

## Slide 8: Approach
Milestone 1 – Provide Transaction Data for TC (Q1, 2018)
  Sources all block and allocation transaction data for TC
  Supports ability to do Order Fill Allocations by Distribution Desk
  Expands lifecycle and historical information for transaction data
  Status – In Client Beta for Testing

## Slide 9: Milestones
Milestone 1 - Provide all position impact transactions for PORT analytics (Q4, 2017)
  Upload batch transactions for POINT Clients
  Apply Corp Actions and aggregate position impacts for use in PORT
  Allow adjustments to uploaded position impact transactions
  Upload starting positions
  Allow position and portfolio resets
  Migrate all POINT transaction clients to TMS platform
  Status: Clients are being on-boarded, in production.
Milestone 2 - AIM integration with BRAIS (2018, TBD)
  Aggregate AIM position impact transactions for use in PORT BRAIS Analytics

## Slide 10: Assumptions
Milestone 1 - Integrate with TMS (Q2, 2018)
  Publish and record all TOMS tickets, natively
  Use it for MIFID after Jan’ 18
Milestone 2 - Blotters using TMS (Q3, 2018)
  Read and write tickets natively from TMS
Milestone 3 - Use MTS for downstream processes (TBD)
  Provide Trade feeds and reporting
Milestone 4 - Position Keeping (TBD)
  Record position impacts

## Slide 11: Risks
Milestone 1 – TOMS to book OTC Derivatives in TMS for a single asset class (Q2, 2018)
  Version Trade/Contract along with lifecycle events for Swaps and be-spoke derivatives
  Record cashflows due to lifecycle events
Milestone 2 – Trade History (Q3, 2018)
  Provide history of trade and contract changes
Milestone 3 – MARS Integration (Q2/Q3, 2018)
  Integrate with MARS for valuation
Milestone 4 - Integrate EOD Processing (Not planned as yet)
  Read transactions from MTS
  Generate actual cashflows/coupon payments and store it in TMS
  Generate/store position impacts for PnL

## Slide 12: APPENDIX A
Trades (Can be modeled under the trade model, without much variation):
  - Equities
  - Vanilla fixed income (Corps, Munis, etc)
  - Options
  - Futures
  - Index
  - Mortgages
  - FX (spot, forwards)
  - Swaps (inclusive of CFDs)
  - Loans
  - Commodities
  - Money Markets / Repos / Overnight or Term Deposits\
- Transfers
  - Cash deposit/withdrawal/transfer
  - Asset Transfers
  - Journals (addition of securities without a specific trade attached)
- Coupon Payments and Cash flows (for lack of a better term)
  - Splits
  - Dividends
  - Coupons
  - Defaults

## Slide 13: APPENDIX B
trade2.f|-> update transaction (accftrn)
|-> notify middle office (ok_release)
|-> send trade feed (sendtkt2)
|-> update position (create.f -> accfpdb/hpos)
|-> send position feed
|-> update cash database (ufpssumm2)
|-> update compliance